## Release
Name | Description | Release Type | Start Date | End Date | Status | Type Of Testing | Priority | Responsibility
Release 5_Dec3_to_5 | Release 5_Dec3_to_5 | Major | 03-Dec-2018 | 07-Dec-2018 |  | Web based/Client server/Desktop | High | Saugata Kumar

## Sprint
ID | Name | Description | SprintType | Start Date | End Date | Release | Sprint Duration | Status | Responsibility
SPR6 | 7th Dec Sprint | 7th Dec Sprint | Functional Testing - Manual | 03-Dec-2018 | 07-Dec-2018 | Release 5_Dec3_to_5 | User Defined | Open | Saugata Kumar

## User Story
Name | Description | Card Owner | User Story Type | State | Due Date | Priority | Theme | Epic | Release | Sprint | Actual end Date | Estimate Story Points | Actual Story Points | Resource Group | Sprint type | Rank
7th Dec Release - Investment | 7th Dec Release - Investment | Amritesh Khan (149306) | Functional Testing - Manual | Planned | 07-Dec-2018 | Medium | None | None | Release 5_Dec3_to_5 | 7th Dec Sprint | 07-Dec-2018 | 700 | 700 | All Team Member | Functional Testing - Manual | 0
7th Dec Release - Marketing | 7th Dec Release - Marketing | Gour Karmakar (169590) | Functional Testing - Manual | Planned | 07-Dec-2018 | Medium | None | None | Release 5_Dec3_to_5 | 7th Dec Sprint | 07-Dec-2018 | 540 | 540 | All Team Member | Functional Testing - Manual | 0
7th Dec Release - Distribution | 7th Dec Release - Distribution | Debasree Sen (550371) | Functional Testing - Manual | Planned | 07-Dec-2018 | Medium | None | None | Release 5_Dec3_to_5 | 7th Dec Sprint | 07-Dec-2018 | 480 | 480 | All Team Member | Functional Testing - Manual | 0
7th Dec Release - Digital | 7th Dec Release - Digital | Shawon Mondal (140306) | Functional Testing - Manual | Planned | 07-Dec-2018 | Medium | None | None | Release 5_Dec3_to_5 | 7th Dec Sprint | 07-Dec-2018 | 300 | 300 | All Team Member | Functional Testing - Manual | 0

## Task-Distribution
User Story Name | Name | Current State | Standard Code | To-Do Owner | Estimated Effort | Actual Effort | Remaining Effort | Time Tracking
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Debasree Sen | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Debasree Sen | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Debasree Sen | 40 | 0 | 40
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Agnibha Malakar | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Agnibha Malakar | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Agnibha Malakar | 40 | 0 | 40
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Ceenali Mohanty | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Ceenali Mohanty | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Ceenali Mohanty | 40 | 0 | 40
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Shaik Vajid Basha | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Shaik Vajid Basha | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Shaik Vajid Basha | 40 | 0 | 40
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Subhadeep Chatterjee | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Subhadeep Chatterjee | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Subhadeep Chatterjee | 40 | 0 | 40
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Sananda Jana | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Sananda Jana | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Sananda Jana | 40 | 0 | 40
7th Dec Release - Distribution | Develop Test Scenario | Open | Test Scenario | Sandip Basak | 20 | 0 | 20
7th Dec Release - Distribution | Develop Test data for test execution | Open | Test Data Setup | Sandip Basak | 20 | 0 | 20
7th Dec Release - Distribution | Perform Test Execution | Open | Testing | Sandip Basak | 40 | 0 | 40

## Task-Marketing
User Story Name | Name | Current State | Standard Code | To-Do Owner | Estimated Effort | Actual Effort | Remaining Effort | Time Tracking
7th Dec Release - Marketing | Develop Test Scenario | Open | Test Scenario | Darpan Chatterjee | 20 | 0 | 20
7th Dec Release - Marketing | Develop Test data for test execution | Open | Test Data Setup | Darpan Chatterjee | 20 | 0 | 20
7th Dec Release - Marketing | Perform Test Execution | Open | Testing | Darpan Chatterjee | 40 | 0 | 40
7th Dec Release - Marketing | Develop Test Scenario | Open | Test Scenario | Debanjan Basu | 20 | 0 | 20
7th Dec Release - Marketing | Develop Test data for test execution | Open | Test Data Setup | Debanjan Basu | 20 | 0 | 20
7th Dec Release - Marketing | Perform Test Execution | Open | Testing | Debanjan Basu | 40 | 0 | 40
7th Dec Release - Marketing | Develop Test Scenario | Open | Test Scenario | Deep Bhowmick | 20 | 0 | 20
7th Dec Release - Marketing | Develop Test data for test execution | Open | Test Data Setup | Deep Bhowmick | 20 | 0 | 20
7th Dec Release - Marketing | Perform Test Execution | Open | Testing | Deep Bhowmick | 40 | 0 | 40
7th Dec Release - Marketing | Develop Test Scenario | Open | Test Scenario | Gour Karmakar | 20 | 0 | 20
7th Dec Release - Marketing | Develop Test data for test execution | Open | Test Data Setup | Gour Karmakar | 20 | 0 | 20
7th Dec Release - Marketing | Perform Test Execution | Open | Testing | Gour Karmakar | 40 | 0 | 40
7th Dec Release - Marketing | Develop Test Scenario | Open | Test Scenario | Sony Goswami | 20 | 0 | 20
7th Dec Release - Marketing | Develop Test data for test execution | Open | Test Data Setup | Sony Goswami | 20 | 0 | 20
7th Dec Release - Marketing | Perform Test Execution | Open | Testing | Sony Goswami | 40 | 0 | 40

## Task-Investment
User Story Name | Name | Current State | Standard Code | To-Do Owner | Estimated Effort | Actual Effort | Remaining Effort | Time Tracking
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Subhajit Saha | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Subhajit Saha | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Subhajit Saha | 40 | 0 | 40
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Prachetosh Ghosh | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Prachetosh Ghosh | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Prachetosh Ghosh | 40 | 0 | 40
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Samarjit Dey | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Samarjit Dey | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Samarjit Dey | 40 | 0 | 40
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Rituraj Purkayastha | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Rituraj Purkayastha | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Rituraj Purkayastha | 40 | 0 | 40
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Amritesh Khan | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Amritesh Khan | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Amritesh Khan | 40 | 0 | 40
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Sreemoyee Roy | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Sreemoyee Roy | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Sreemoyee Roy | 40 | 0 | 40
7th Dec Release - Investment | Develop Test Scenario | Open | Test Scenario | Himadri Dey | 20 | 0 | 20
7th Dec Release - Investment | Develop Test data for test execution | Open | Test Data Setup | Himadri Dey | 20 | 0 | 20
7th Dec Release - Investment | Perform Test Execution | Open | Testing | Himadri Dey | 40 | 0 | 40

## Task-Digital
User Story Name | Name | Current State | Standard Code | To-Do Owner | Estimated Effort | Actual Effort | Remaining Effort | Time Tracking
7th Dec Release - Digital | Develop Test Scenario | Open | Test Scenario | Shawon Mondal | 20 | 0 | 20
7th Dec Release - Digital | Develop Test data for test execution | Open | Test Data Setup | Shawon Mondal | 20 | 0 | 20
7th Dec Release - Digital | Perform Test Execution | Open | Testing | Shawon Mondal | 40 | 0 | 40
7th Dec Release - Digital | Develop Test Scenario | Open | Test Scenario | Ankita Chatterjee | 20 | 0 | 20
7th Dec Release - Digital | Develop Test data for test execution | Open | Test Data Setup | Ankita Chatterjee | 20 | 0 | 20
7th Dec Release - Digital | Perform Test Execution | Open | Testing | Ankita Chatterjee | 40 | 0 | 40
7th Dec Release - Digital | Develop Test Scenario | Open | Test Scenario | Swarup Roy | 20 | 0 | 20
7th Dec Release - Digital | Develop Test data for test execution | Open | Test Data Setup | Swarup Roy | 20 | 0 | 20
7th Dec Release - Digital | Perform Test Execution | Open | Testing | Swarup Roy | 40 | 0 | 40
7th Dec Release - Digital | Develop Test Scenario | Open | Test Scenario | Anusree Barat | 20 | 0 | 20
7th Dec Release - Digital | Develop Test data for test execution | Open | Test Data Setup | Anusree Barat | 20 | 0 | 20
7th Dec Release - Digital | Perform Test Execution | Open | Testing | Anusree Barat | 40 | 0 | 40
7th Dec Release - Digital | Develop Test Scenario | Open | Test Scenario | Dipanita Maity | 20 | 0 | 20
7th Dec Release - Digital | Develop Test data for test execution | Open | Test Data Setup | Dipanita Maity | 20 | 0 | 20
7th Dec Release - Digital | Perform Test Execution | Open | Testing | Dipanita Maity | 40 | 0 | 40
7th Dec Release - Digital | Develop Test Scenario | Open | Test Scenario | Esha Sen | 20 | 0 | 20
7th Dec Release - Digital | Develop Test data for test execution | Open | Test Data Setup | Esha Sen | 20 | 0 | 20
7th Dec Release - Digital | Perform Test Execution | Open | Testing | Esha Sen | 40 | 0 | 40